## PLAN
Kaizen Leader Standard Work - Kaizen PLAN
|  | WHEN? |  |  |  | Status
Activitity (What?) |  | Weeks out before Kaizen
|  | 4 wks | 3 wks | 2 wks | 1 wk
1 | Complete Kaizen Charter, review w/ Champion and OpEx Facilitator, get charter signoffs | X
2 | Review baseline metrics and financial impact w/ OpEx Facilitator, Champion and Controller | X
3 | Determine Kaizen Team Members, approve with respective managers, contact all team members and ensure their availability for long days during Kaizen week | X
4 | Initiate Stakeholder Analysis and Communication Plan | X
5 | Review Kaizen Week activities and Charter with Team Members |  | X
6 | Determine extended team needs (ie: maintenance, safety, suppliers, etc.) - Work w/ Champion to secure availability |  | X
7 | Work w/ Production, Logistics, OpEx Facilitator, and Champion to create plan for any potential significant downtime during Kaizen week |  | X
8 | Understand Safety and Quality Assurance requirements and ensure these functions have involvement if applicable |  |  | X
9 | Work w/ OpEx Facilitator to arrange for a Kaizen team "WAR ROOM" and the necessary office supplies, ie: flip charts, markets, projector, etc… |  |  | X
10 | Determine what improvement supplies are needed for Kaizen event, ie: label maker tape, signs, parts bins, racks, visual management boards, floor tape, etc… (If items need to be purchased, work with Kaizen Facilitator) |  |  |  | X
11 | Review and share Kaizen improvements and impacts that will be made during Kaizen Week w/ other employees of the process under study |  |  |  | X
12 | Post Charter in Kaizen area and annouce to area members | X
13 | Ensure visual management supplies i.g. 5S tape, signage, visual management boards, etc. have been ordered or are in stock |  |  | X
14 | Coordinate for Friday report out presentation times and send respective invitations to leadership |  |  | X
15 | Review Status of Stakeholder Analysis and Communication Plan |  |  | X
16 | Follow up with Logistics and Production to ensure a plan is in place if there will be significant downtime during Kaizen week |  |  | X
17 | Arrange lunch for the duration of the kaizen |  |  |  | X
18 | Review any last minute issues or concerns w/ OpEx Facilitator and Champion |  |  |  | X
19 | Contact all Kaizen members to ensure their readiness for the Kaizen event (If applicable, send out invites via email) |  |  |  | X

## DO
Kaizen Leader Standard Work - Kaizen DO
|  | WHEN? |  |  |  |  | Status
Activitity (What?) |  | Kaizen Week Days
|  | Mon | Tue | Wed | Th | Fr
1 | Review Charter w/ Team | X
2 | Create Agenda Kaizen Newspaper - Day 1 | X
3 | Review Stakeholder Analysis and Communication Plan w/ Team | X
4 | Measure the Current Process as it exists today | X
5 | Discuss existing baseline metrics | X
6 | Current Layout | X
7 | Spaghetti Diagram | X
8 | 5S Audit, including pictures | X
9 | Waste Walk Observations | X
10 | Determine Work Sequence (i.e. process map) | X
11 | Time Observations | X
12 | Go and See | X
13 | Review Current Standard Work or SOP | X
14 | Create ABCD - Day 1 | X
15 | Create Agenda Kaizen Newspaper - Day 2 | X
16 | Review Agenda Kaizen Newspaper - Day 2 |  | X
17 | Identify Gaps between the process today and the future state |  | X
18 | Design/develop new proccess to addresses waste observations, spaghetti diagram observations, 5S audit, etc. |  | X
19 | Create Implementation Plan |  | X
20 | Simulate improvements with minor change and work aids |  | X
21 | Identify Gaps and develop new implementation plan |  | X
22 | Create ABCD - Day 2 |  | X
23 | Create Agenda Kaizen Newspaper - Day 3 |  | X
24 | Review Agenda Kaizen Newspaper - Day 3 |  |  | X
25 | Implement new process (physical changes) |  |  | X
26 | Create new standard work |  |  | X
27 | Train operators on new standard work |  |  | X
28 | Stabilize new process |  |  | X
29 | Collect time observations for new process |  |  | X
30 | Create new balance charts, etc. |  |  | X
31 | Make refinements |  |  | X
32 | Pursue Perfection by improving on the new ideas |  |  | X
33 | Assess improvements for EHS, and Quality Concerns |  |  | X
34 | Create ABCD - Day 3 |  |  | X
35 | Create Agenda Kaizen Newspaper - Day 4 |  |  | X
36 | Review Agenda Kaizen Newspaper - Day 4 |  |  |  | X
37 | Review Agenda - Day 4 |  |  |  | X
38 | Final Changes are made |  |  |  | X
39 | Measure the improvements |  |  |  | X
40 | 5S Audit |  |  |  | X
41 | After Pictures |  |  |  | X
42 | Compare with baseline metrics |  |  |  | X
43 | Develop Control Plans: |  |  |  | X
44 | – Standard Work |  |  |  | X
45 | – Visual Management |  |  |  | X
46 | – Communication Plan |  |  |  | X
47 | Discuss final metrics with facilitators and Financial controllers |  |  |  | X
48 | Create 30 Day Action List (Newspaper) if applicable |  |  |  | X
49 | Create Final Report Presentation |  |  |  | X
50 | Practice Report Out |  |  |  | X
51 | Create ABCD - Day 4 |  |  |  | X
52 | Create Agenda Kaizen Newspaper - Day 5 |  |  |  | X
53 | Review Agenda Kaizen Newspaper - Day 5 |  |  |  |  | X
54 | Present Results to Leadership |  |  |  |  | X
55 | Celebrate |  |  |  |  | X

## CHECK-ACT
Kaizen Leader Standard Work - Kaizen CHECK/ACT
|  | WHEN? |  |  |  | Status
Activitity (What?) |  | Weeks after Kaizen
|  | Wk1 | Wk2 | Wk3 | Wk4
1 | Attend daily stand up/communication meetings | X
2 | Create and implement audit checklists for Standard Work and 5S | X
3 | Conduct daily Standard Work and 5S audits with process owner | X
4 | Understand performance metrics for the new state | X
5 | Review and discuss issues and problems identified during audits, inclusive of Quality, Safety, etc… | X
6 | Review performance metrics and initiate countermeasures | X
7 | Visually display and report trends for performance metrics and audit results | X
8 | Ensure transition plan for new state is being followed (new standard work, new performance metrics, new headcount plan, etc…) | X
9 | Aid in achieving visible management support with daily walkabouts on all shifts | X
10 | Attend daily stand up/communication meetings |  | X
11 | Ensure audits to standard work and 5S are being conducted by process owner, results are being discussed and visually displayed |  | X
12 | Ensure performance metrics are visually displayed and trends are being reported |  | X
13 | Ensure countermeasures are being implemented and results posted |  | X
14 | Ensure transition plan for new state is being followed (new standard work, new performance metrics, new headcount plan, etc…) |  | X
15 | Aid in achieving visible management support with daily walkabouts on all shifts |  | X
16 | Conduct weekly meeting with Kaizen team to review Kaizen Newspaper (30 day list) progress and metrics to ensure sustainability |  | X
17 | Track % Complete for 30 day action list - Communicate with team |  | X
18 | Understand metrics and financial impact |  | X
19 | Attend daily stand up/communication meetings |  |  | X | X
20 | Ensure audits to standard work and 5S are being conducted by process owner, results are being discussed and visually displayed |  |  | X | X
21 | Ensure performance metrics are visually displayed and trends are being reported |  |  | X | X
22 | Ensure countermeasures are being implemented and results posted |  |  | X | X
23 | Ensure transition plan for new state is being followed (new standard work, new performance metrics, new headcount plan, etc…) |  |  | X | X
24 | Aid in achieving visible management support with daily walkabouts on all shifts |  |  | X | X
25 | Conduct weekly Meeting with team to review Kaizen Newspaper (30 day list) progress and metrics to ensure sustainability |  |  | X | X
26 | Meet with Champion and OpEx Facilitator to discuss sustainment in the area of the event |  |  | X | X
27 | Attend hand off Meeting with Process Owner, Champion, OpEx facilitator, and Leadership team present |  |  | X | X
28 | Attend financial summary meeting |  |  | X | X
29 | Ensure financials have been reported, communicated to team members and are visually displayed |  |  | X | X